## Sheet1
Study Location: | O:\Projects\iSAFE\iSAFE_Dev\safety_analysis_1014\v_work\data\derived\SGNTUC-016\pgms
UserID: | Alex Tian
Date performed | Test Decription | Expected Results | Devations from expected results or any unexpected behaviors. Leave blank if no findings. | Developer Response | Resolution Date
2023-04-20 | Open the SAS launcher in the programs folder of the selected programs. Submit the identified programs in parallel using the best server options. Check the box to receive a notification on completion | The jobs submit in parallel in batches sizes calculated from the available CPU. The app selects the most available server for each batch (note the app give a bias to prod so it's not a cpu to cpu comparison) The HTML summary is displayed in the default browser when the programs complete. A notification is sent to the user with a high-level summary of the results | I see this error from time to time when running programs in parralel: Test location: O:\Projects\iSAFE\iSAFE_Dev\safety_analysis_1014\v_work\data\derived\SGNTUC-016\pgms | Study-level macro accessing the same Excel file in parallel using this libname statement: libname xdb pcfiles path="O:\Projects\iSAFE\docs\Data Harmonization Metadata.xlsx"; caused a concurreny issue. The solution is to run programs with these dependencies sequentially. It might be possible to alter the macro or SS to prevent concurrency locks. SPI will look into that but this is not an error in SJM.
2023-04-20 | Submit the same programs using sequential mode on the stage server. | The app submits the programs sequentially on the stage server.
2023-04-20 | Using the folder navigator to select the testing folder. Select the QC program for one of the programs you ran in the previous step. Select IsQC in the right-side of the program list box for that program and submit. | The HTML summary details the QC results for the QC program. | This error appears in parralel sometimes. | see above
2023-04-20 | Navigate back to the production program. Select a program that has a least one call to a departmental macro. Ideally choose a smaller program as this step can take a while. Select that program and check the box for Resolve SAS Code. Submit the program. When it completes, observe the corresponding file under pgms\resolved. Rename the file by adding '-resolved' to the name and copy the file to the pgms folder. Attempt to run using RunSAS | The code in the new file has no external macro references or %include statements. The formatting is acceptable. Record any sections that appear odd. The program executes as expected. NOTE: due to infinite variability in code, some elements might not format perfectly. | Error below: | This is a parsing issue in the Resolved code formatter. 'if1and' should be 'if 1 and'. Need to add some kind of keyword tokenizer to prevent resolved code from loosing spaces between syntax elements.