## Summary
Attributes | Description
Utility Name: | SAS Job Manager Client Job Launcher
Utility Version: | 2.1
User Guide: | User Guide
Overall Status | Pass
Production Version Date | 2023-10-17
| Owner | Date Completed
Approval for Technical Design (SPI Head or Designee): | Matt Ness
Testing (Developer): | Shawn Hopkins | 17Oct2023
DocuSign P11 Sign Off (After Production Steps Completed)
Role | Owner | Signature (Docu Sign)
Reviewer/Developer: | Shawn Hopkins
SPI Head or Designee: | Matt Ness

## Testing_Data
Testing data used for Unit Tests (where applicable) and Developer_UI_Tests
Version | Testing Data Type | Locations | Description of Test Data
2.1 | Mock Data | O:\Projects\Training\sjm\automation\v1\data\adam\pgms | .BAT file that corresponds to an entry in the SJM Scheduler database

## Unit_Tests
| Requirements: | Specifications (Section 3.1.2)
| Unit Tests: | Unit Tests
| Test Summary: | Test Harness
Version | Test Name | Description | Test ID | Requirement ID | Status
2.1 | Post_RunClient_Success | Integration test creates an instance of the web server and call the runclient endpoint with a valid argument. The HTTP response code is 200 and the endpoint returns the success response | UT.API.01.01 | API01.01 | Pass
2.1 | Post_RunClient_FailUser | Integration test creates an instance of the web server and call the runclient endpoint with a valid argument. The HTTP response code is 200 and the endpoint returns ERROR message that indicates the user is not listed in -U | UT.API.02.01 | API02.01 | Pass
2.1 | Post_RunClient_FailU | Integration test creates an instance of the web server and call the runclient endpoint with a valid argument. The HTTP response code is 200 and the endpoint returns ERROR message that indicates -U is not defined in the .bat file | UT.API.02.02 | API02.01 | Pass
2.1 | Post_RunClient_FailN | Integration test creates an instance of the web server and call the runclient endpoint with a valid argument. The HTTP response code is 200 and the endpoint returns ERROR message that indicates -n is set to true in the bat file | UT.API.02.03 | API02.01 | Pass

## UAT
Test Script: |  | O:\stat_prog_infra\testing\sjm\mcr_spi_launch_sjm_job\v01\data\adam\pgms\v-mcr_spi_launch_sjm_job.sas
Test Data: (requires default security) |  | O:\Projects\Training\sjm\automation\v1\data\adam\pgms
UserID |  | shopkins
Date performed | Test ID | Test Decription | Expected Results | Devations from expected results or any unexpected behaviors. Record "Pass" if no findings. | Developer Response | Resolution Date
2023-10-12 | UAT.01.01 | Successfully launch a job defined in the SJM scheduler | Notice in the log indicates the job was successfully launched. The macro variable SPI_SJM_LAUNCH_YN=Y | Pass
2023-10-12 | UAT.02.01 | Job fails because of invalid user | ERROR in the log indicates user is not authorized to launch the job. The macro variable SPI_SJM_LAUNCH_YN=N | Pass
2023-10-12 | UAT.03.01 | Job fails because -u is not specified in the .BAT file | ERROR in the log indicates -u is not specified in the .BAT file. The macro variable SPI_SJM_LAUNCH_YN=N | Pass
2023-10-12 | UAT.04.01 | Job fails because -n is not specified as true in the .BAT file | ERROR in the log indicates -n is not specified in the .BAT file. The macro variable SPI_SJM_LAUNCH_YN=N | Pass
2023-10-12 | UAT.05.01 | Job fails because he value of job does not match an entry in the DB | ERROR in the log indicates the job could not be found. The macro variable SPI_SJM_LAUNCH_YN=N | Pass
2023-10-12 | UAT.06.01 | Job fails because he value of job is missing | ERROR in the log indicates IN_JOB is a required parameter. The macro variable SPI_SJM_LAUNCH_YN=N | Pass

## Validation
Validation Summary (to Be Completed by Reviewer and Developer):
Review ID | Description of Validation | Expected Results | Validation Findings | Developer Response | Validation Result (Pass/Fail) | Validation Completion Date
C1-03 | Review user guide | Content is accurate |  |  | Pass | 10/17/2023
C1-04 | Review program code | It meets coding standards (e.g., use standard header, assign a correct version ID, use indentation, have good inline documentation, etc.) |  |  | Pass | 10/17/2023
C1-06 | Review testing cases and testing results (log, input, output, etc.) | They are adequate and completed with expected results |  |  | Pass | 10/17/2023
C1-07 | Review UDF (Summary, Testing, Validation) | Documentation is completed and dates are up to date |  |  | Pass | 10/17/2023

## Production
Production Summary (to Be Completed by Developer):
Step# | Description of Production Step | Expected Results | Production Result (Pass/Fail) | Production Completion Date
P01 | Obtain an approval for production from SPI Head or Designee | Approval communicated by SPI Head or Designee | Pass
P04 | Commit the source code to production versioning repository | Ccommitted to remote version control solution | Pass
P05 | Release the corresponding version of the user guide to all intended users (SharedPoint Website) | User guide content is accurate; all hyperlinks work. The user guide can be accessed from the SPI SharedPoint homepage | Pass
P12 | Initiate P11 Docusign | Docusign document is approved and stored on the SPI SPO site | NA | NA